## Sheet1
PROJECT | ASSIGNEE | AUDIENCE | ISSUES,DELAYS/ POSSIBLE SOLUTIONS | STATE | PLANNED COMPLETION DATE | ACCOMPLISHMENTS | TASK ACCOMPLISHMENT DATE
Co-operative | Musideen Michael Samad | •Primera Credit Microfinance Bank(PMB) •Co-operative | Issue 1: Incomplete software requirements. Who are the users of the system and what are their access privileges. When a staff is repaying a lump sum less than the expected lump sum for different Micro-finance bank the staff obtained a loan from, what ratio should be used to divide the lump sum, so each bank gets the appropriate amount . Apart from the expected repayment file upload, actual repayment file upload and the necessary subtractions(i.e difference computation), what other functionalities are required of the system. What are the views the users wants to see. Are all the stakeholders in sync with the system requirements. | Working on •Expected repayment upload •Actual Repayment upload •Difference computation •Record views •Search | Week 31 | •User Profiling(100% completed) | 5th July, 2016 - 7th July,2016